## Total
Date | Amount paid (Rs)
| 15000 | Advance |  | Architect
2018-06-11 | 60500 | 1.5% |  | Architect
2018-12-11 |  |  | 9500 | Corporation expense
2019-02-01 | 50000 |  |  | THADIPPANI ADVANCE (Josettan)
19/1/19 |  |  |  | 10000 advance received from Jain for demolishing
28/1/19 | 9200 |  |  | Compound Net
28/1/19 | 200000 |  |  | Advance given to Martin, Civil Contractor
2019-01-02 |  |  |  | 50000 balance received from Jain for demolishing
2019-09-03 | 20220 |  |  | 0.5% to ARCHITECT
15/3/19 | 150000 |  |  | Cheque given to Martin
15/3/19 | 200000 |  |  | Cheque given to Martin
2019-05-04 | 70000 |  |  | paid to Josettan
2019-05-04 | 300000 |  |  | paid to Martin
19/4/19 | 100000 |  |  | paid to Josettan (reached ഉരുപ്പടി of ground floor)
2019-03-05 | 250000 |  |  | paid to Martin
2019-07-06 | 300000 |  |  | paid to Martin
21/6/19 | 5000 |  |  | paid to Aneesh
21/6/19 | 6200 |  |  | concrete wiring plumbing
21/6/19 | 1100 |  |  | Concreting tip
21/6/19 | 3600 |  |  | Concreting food
2019-08-07 | 125000 |  |  | paid to Martin (cheque)
18/7/19 | 100000 |  |  | paid to Josettan
22/7/19 | 63500 |  |  | paid to Josettan
24/7/19 | 300000 |  |  | paid to Martin in cash
16/8/19 | 5000 |  |  | paid to Aneesh
17/8/19 | 6000 |  |  | paid to Aneesh
16/8/19 | 12499 |  |  | paid to Tom Pipes (wiring pipes)
21/8/19 | 7000 |  |  | paid to Aneesh
21/8/19 | 12141 |  |  | wiring accessories (thanickal)
25/8/19 | 5000 |  |  | paid to interior designer
2019-05-09 | 400000 |  |  | paid to Martin
2019-05-09 | 5000 |  |  | paid to Aneesh
2019-07-09 | 5000 |  |  | paid to Aneesh
2019-09-09 | 7000 |  |  | paid to Aneesh
27/9/19 | 5000 |  |  | paid to Aneesh
27/9/19 | 4000 |  |  | shop - roof concreting wiring materials
27/9/19 | 1300 |  |  | concreting - tip
28/9/19 | 178800 |  |  | paid to Martin (cheque - shop)
29/9/19 | 2000 |  |  | well maintenance
30/9/19 | 6500 |  |  | well maintenance
2019-01-10 | 200000 |  |  | paid to Martin
2019-03-10 | 15000 |  |  | Anchala
2019-07-10 | 10000 |  |  | interior
2019-10-10 | 2000 |  |  | paid to Aneesh
2019-11-10 | 1050 |  |  | Corporation permit fee remitted
2019-12-10 | 8000 |  |  | paid to Aneesh
2019-12-10 | 900 |  |  | wiring accessories
18/10/19 | 3000 |  |  | paid to Aneesh
19/10/19 | 6000 |  |  | paid to Aneesh
19/10/19 | 9851 |  |  | wiring materials (thanickal)
26/10/19 | 400000 |  |  | paid to Martin
26/10/19 | 11000 |  |  | paid to Anish
30/10/19 | 3000 |  |  | paid to Anish
31/10/19 | 3000 |  |  | paid to Anish (Plumbing)
31/10/19 | 29593 |  |  | Sanitory items
2019-01-11 | 1300 |  |  | electrical wiring accessories
2019-02-11 | 6000 |  |  | paid to Anish (Plumbing)
2019-02-11 | 12000 |  |  | paid to Anish
2019-02-11 | 8690 |  |  | plumbing materials
2019-02-11 | 11200 |  |  | Closet
2019-04-11 | 43443 |  |  | paid to Toms Pipe (Plumbing materials)
2019-06-11 | 50550 |  |  | paid to Architect
2019-09-11 | 8000 |  |  | paid to Aneesh
2019-07-11 | 3000 |  |  | paid to Aneesh (Plumbing)
2019-07-11 | 1140 |  |  | plumbing accessories (local)
2019-08-11 | 4000 |  |  | paid to Aneesh (Plumbing)
2019-09-11 | 4000 |  |  | paid to Aneesh (Plumbing)
2019-09-11 | 29593 |  |  | Sanitary Items
2019-09-11 | 5000 |  |  | Welding - grill - Advance
15/11/19 | 200000 |  |  | paid to Martin
15/11/19 | 5000 |  |  | paid to Anees (Plumbing)
15/11/19 | 1000 |  |  | wiring/plumbing materials
16/11/19 | 5000 |  |  | paid to Aneesh (Electrical)
16/11/19 | 8000 |  |  | paid to Anees (Plumbing)
21/11/19 | 20000 |  |  | Advance for Kitchen Cabinet work
23/11/19 | 6000 |  |  | Grid welding balance
23/11/19 | 4000 |  |  | Paid to Aneesh (Plumbing)
23/11/19 | 390 |  |  | plumbing materials
28/11/19 | 12500 |  |  | paid to Saimon for out Stair Metal works - Advance
30/11/19 | 2000 |  |  | paid to Aneesh (Plumbing)
2019-04-12 | 481 |  |  | electrical - concreting
2019-05-12 | 3000 |  |  | paid to Aneesh (wiring)
2019-05-12 | 1600 |  |  | Concreting tip
2019-05-12 | 1100 |  |  | Concreting Food
2010-06-12 | 300000 |  |  | paid to Martin in cash
2019-06-12 | 200000 |  |  | paid to Martin by Cheque (2 Leaves)
2019-11-12 | 13000 |  |  | False Ceiling (Advance paid to Shibu)
2019-11-12 | 30000 |  |  | External stair - paid to Saimon
14/12/19 | 3000 |  |  | paid to Aneesh (Electrical) PCC Concrete
16/12/19 | 110000 |  |  | paid to Sanoj for Interior
21/12/19 | 15000 |  |  | paid to Saimon (to his staff) hand rail - outside stair
21/12/19 | 200000 |  |  | paid to Martin
26/12/19 | 20000 |  |  | Anjala (Concrete Janal)
27/12/19 | 5000 |  |  | paid to Aneesh (Electrical)
27/12/19 | 500 |  |  | tip to Annan
30/12/19 | 50000 |  |  | Advance paid to ABC Emlprium - Tile
2020-02-01 | 5000 |  |  | paid to Aneesh (Electrical)
2020-02-01 | 20000 |  |  | paid to Aneesh Aluminum Fabrn (Handrail internal)
2020-04-01 | 7000 |  |  | paid to Anish (Electrical)
2020-04-01 | 4600 |  |  | wiring materials ( 2 bills [570+3998])
2020-04-01 | 5000 |  |  | Saimon - welding
2020-06-01 | 1350 |  |  | Tip to Loading Union
2020-06-01 | 88400 |  |  | Balance payment to ABC Emporium +driver tip
2020-09-01 | 3000 |  |  | paid to Anees (Electrical)
2020-09-01 | 79124 |  |  | paid to Vinod (Look Lite) - wire
2020-11-01 | 14000 |  |  | paid to Anees (Electrical)
2020-11-01 | 1180 |  |  | wiring materials (Anees)
2020-11-01 | 300 |  |  | Window grill auto charge
2020-11-01 | 13000 |  |  | paid to Saimon (Step grill work)
14/1/20 | 19000 |  |  | paid to Shibu for balance false ceiling
14/1/20 | 5000 |  |  | paid to Aneesh (Electrical)
15/1/20 | 3500 |  |  | paid to Saimon (Stair hand rail)
15/1/20 | 12745 |  |  | Plumbing Supports ( Hi-Tech)
15/1/20 | 96500 |  |  | Tiles - Sarma Marbles
15/1/20 | 2000 |  |  | Union - Tiles
16/1/20 | 6000 |  |  | paid to Anees (Electrical)
18/1/20 | 13000 |  |  | paid to Anees (Plumbing)
18/1/20 | 900 |  |  | plumbing materials(Anees)
20/1/20 | 300000 |  |  | paid to Martin
20/1/20 | 850 |  |  | paid to ABC Emporium - Tile
20/1/20 | 32296 |  |  | plumbing materials - Madathikudi, Thrippunithura
21/1/20 | 66318 |  |  | Toms Pipes
21/1/20 | 4100 |  |  | Kela Chandra
21/1/20 | 1000 |  |  | paid to Anees, (bill pending)
22/1/20 | 3000 |  |  | paid to Anees (Plumbing)
23/1/20 | 25000 |  |  | Granites
24/1/20 | 5000 |  |  | paid to Aneesh (Plumbing)
25/1/20 | 14000 |  |  | paid to Aneesh (Plumbing)
25/1/20 | 600 |  |  | plumbing materials(Anish-4 bills)
25/1/20 | 9500 |  |  | Anchala (balance paid)
27/1/20 | 12000 |  |  | paid to Saimon (Advance for handrail, terrace)
27/1/20 | 2750 |  |  | hitech supports
27/1/20 | 32000 |  |  | plumbing - flush tank etc.
27/1/20 | 275 |  |  | plumbing items - thrippunithura
27/1/20 | 85000 |  |  | One & Only - Kitchen cabinet
28/1/20 | 2000 |  |  | paid to Aneesh (Plumbing)
29/1/20 | 5000 |  |  | paid to Aneesh (Plumbing)
30/1/20 | 440 |  |  | plumbing pvc ball valves-4nos
31/1/20 | 3000 |  |  | paid to Aneesh (Plumbing)
31/1/20 | 3250 |  |  | plumbing items - thrippunithura
2020-01-02 | 15000 |  |  | paid to Anees (plumbing)
2020-01-02 | 10000 |  |  | paid to Simon - hand rail - balance
2020-01-02 | 4000 |  |  | paid to Anees (Electrical)
2020-05-02 | 10000 |  |  | paid to Anees (plumbing)
2020-07-02 | 13000 |  |  | paid to Aneesh (plumbing).
2020-07-02 | 1577 |  |  | plumbing materials by Anis (3 bills)
2020-07-02 | 30205 |  |  | Stove+Sink
2020-08-02 | 2250 |  |  | Plumbing materials - Thrippunithura
2020-10-02 | 15000 |  |  | Hand rail work - Anish.
2020-10-02 | 15000 |  |  | paid to Aneesh Aluminum Fabrn (Handrail internal)
2020-11-02 | 20000 |  |  | Advance paid - Dline(Door)
2020-12-02 | 3000 |  |  | paid to Anees (Plumbing)
13/2/20 | 2000 |  |  | paid to Anees (Plumbing)
15/2/20 | 11000 |  |  | paid to Saimon (Settled tank stand & Terrace hand rail)
15/2/20 | 9000 |  |  | paid to Anees (Plumbing)
15/2/20 | 917 |  |  | plumbing materials ( two bills)
16/2/20 | 2000 |  |  | paid to Anees (Plumbing)
18/2/20 | 7499 |  |  | plumbing (Toms Pipes)
19/2/20 | 5000 |  |  | paid to Anees (Plumbing)
21/2/20 | 2000 |  |  | paid to Shibu (False ceiling)
21/2/20 | 29950 |  |  | Ellis switch
21/2/20 | 3000 |  |  | Bible verse
21/2/20 | 1698 |  |  | plumbing pipe etc by Anees 2 bills
21/2/20 | 5000 |  |  | paid to Saimon as Advance to next work (ladder to water tank)
22/2/20 | 12000 |  |  | paid to Anees (Plumbing)
22/2/20 | 2000 |  |  | paid to Anees (Electrical)
22/2/20 | 330 |  |  | plumbing materials
22/2/20 | 841 |  |  | led strip
22/2/20 | 500 |  |  | false ceiling
25/2/20 | 11400 |  |  | Key purchase - Divine Marketing
25/2/20 | 400000 |  |  | paid to Martin
26/2/20 | 6000 |  |  | paid to Anees ( plumbing)
26/2/20 | 2000 |  |  | plumbing materials by Anees
27/2/20 | 15000 |  |  | TV unit
28/2/20 | 2000 |  |  | paid to Anees (Plumber)
28/2/20 | 6000 |  |  | paid to Saimon (balance for Solar stand & water tank ladder)
28/2/20 | 20000 |  |  | paid to Saimon(Advance for Gate)
28/2/20 | 500 |  |  | Concrete door hinges
29/2/20 | 15000 |  |  | Anees Plumbing
29/2/20 | 8478 |  |  | Glass
29/2/20 | 2474 |  |  | Anees 4 bills
2020-02-03 | 1000 |  |  | Anees Plumbing
2020-02-03 | 4281 |  |  | Tom pipes
2020-04-03 | 2774 |  |  | Anees 3 bills
2020-04-03 | 4000 |  |  | Anees Plumbing
2020-06-03 | 5974 |  |  | Tom Pipes
2020-07-03 | 3000 |  |  | Anees Electrical
2020-07-03 | 12000 |  |  | Anees Plumbing
2020-09-03 | 1000 |  |  | Anees Plumbing
2020-09-03 | 25000 |  |  | Divine door
2020-10-03 | 1035 |  |  | Lock
2020-10-03 | 15000 |  |  | Divine doors
2020-12-03 | 21561 |  |  | Look Lite
14/3/20 | 142 |  |  | Tower bolt
14/3/20 | 40000 |  |  | One & only - balance paid in cash
14/3/20 | 2000 |  |  | Anees - 5 bills
14/3/20 | 780 |  |  | Baby Latch
14/3/20 | 12000 |  |  | Anees Electrical
14/3/20 | 100000 |  |  | Martin
14/3/20 | 69751 |  |  | Toto - Le Platino
14/3/20 | 92960 |  |  | Toto - Le Platino
14/3/20 | 21187 |  |  | Look lite
14/3/20 | 7145 |  |  | Cochin Agencies
15/3/20 | 273055 |  |  | Josettan - Door frames
16/3/20 | 200000 |  |  | Martin
17/3/20 | 21375 |  |  | L & T Breakers
17/3/20 | 390 |  |  | Baby Latch
18/3/20 | 3000 |  |  | Anees Electrical
18/3/20 | 810 |  |  | Rack bolt
18/3/20 | 600 |  |  | Bumatra - wash basin
21/3/20 | 7000 |  |  | Anees Electrical
21/3/20 | 18160 |  |  | ForHome
23/3/20 | 14610 |  |  | Toto - Le Platina
23/3/20 | 3960 |  |  | Toto - Le Platina
23/3/20 | 448 |  |  | Cochin Agencies
29/3/20 | 32500 |  |  | Top floor windows
156191
2020-11-04 | 2000 |  |  | Anees Electrical
2020-12-04 | 869 |  |  | Anees one bill
13/4/20 | 2000 |  |  | Anees Electrical
14/4/20 | 1000 |  |  | Anees Electrical
15/4/20 | 7669 |  |  | Future - Electrical
18/4/20 | 7000 |  |  | Anees Plumbing
18/4/20 | 7000 |  |  | Anees Electrical
19/4/20 | 10360 |  |  | Tony Lights
19/4/20 | 1850 |  |  | Tony Lights
20/4/20 | 50000 |  |  | Toto
23/4/20 | 5556 |  |  | Anees 5 bills
24/4/20 | 75000 |  |  | toto
25/4/20 | 6000 |  |  | Anees Electrical
25/4/20 | 8000 |  |  | Anees Plumbing
25/4/20 | 11119 |  |  | Luker Exhaust fan
27/4/20 | 20000 |  |  | Toto
27/4/20 | 5000 |  |  | Toto
28/4/20 | 898 |  |  | 2 bills
30/4/20 | 434 |  |  | Baby latch
2020-02-05 | 200000 |  |  | Martin
2020-05-05 | 1500 |  |  | Luker Bulb
2020-05-05 | 50000 |  |  | Advance paid to Nilambur Furniture
2020-05-05 | 6500 |  |  | Water Pump
2020-05-05 | 4927 |  |  | Tony Lites
2020-06-05 | 100000 |  |  | Kitchen Cabinet top floor Advance
2020-06-05 | 25000 |  |  | Divine doors
2020-07-05 | 6450 |  |  | Mirror
2020-07-05 | 480 |  |  | Nediyath Sanitory
2020-07-05 | 7695 |  |  | Door - Divine - final balance
2020-07-05 | 49050 |  |  | Light fittings - Luker
2020-07-05 | 1499 |  |  | Future - Anees bill
2020-08-05 | 30300 |  |  | Light fittings - Kottayam
2020-09-05 | 5816 |  |  | Look light Fan+LED bulb
2020-09-05 | 1684 |  |  | Fancy light + calling bell
2020-09-05 | 9000 |  |  | Anees - Electrical
2020-09-05 | 250 |  |  | Welding - motor stand
2020-09-05 | 6000 |  |  | Compiund wall - grill work
2020-09-05 | 6000 |  |  | Simon - Car shed
2020-09-05 | 1600 |  |  | Tile for Dining wash basin - ground floor
2020-11-05 | 1100 |  |  | Tree cutting
2020-12-05 | 3600 |  |  | Fan - Canteen
14/5/20 | 6500 |  |  | UG cables
14/5/20 | 3000 |  |  | Anees plumbing
14/5/20 | 2300 |  |  | two bills by Anees
15/5/20 | 35000 |  |  | paid to Simon
15/5/20 | 200000 |  |  | Martin
16/5/20 | 1135 |  |  | plumbing materials by Anees
16/5/20 | 11000 |  |  | Anees Electrical
16/5/20 | 7295 |  |  | Net meter purchase
17/5/20 | 95000 |  |  | Kitchen cabinet top floor
27/5/20 | 100000 |  |  | Martin
18/5/20 | 2500 |  |  | Corporation staff
18/5/20 | 2100 |  |  | Show wall bulb
19/5/20 | 1120 |  |  | Meter Testing fee
19/5/20 | 3800 |  |  | Divya Sanitations, Vyttila
19/5/20 | 13425 |  |  | Wash basin + tap (top floor)
19/5/20 | 7110 |  |  | Sink - ForHome
19/5/20 | 320 |  |  | Hinges+knobs
20/5/20 | 3000 |  |  | Anees plumbing
20/5/20 | 35000 |  |  | paid to Edison - net advance
21/5/20 | 20000 |  |  | paid to Anson - curtain
21/5/20 | 2700 |  |  | Sofa cleaning
22/5/20 | 40000 |  |  | Interlock Advance
23/5/20 | 11000 |  |  | Anees plumbing
23/5/20 | 9000 |  |  | Car shed balance
23/5/20 | 5000 |  |  | Saimon Gate work
23/5/20 | 50000 |  |  | Nilambur furniture
23/5/20 | 2800 |  |  | 3 bills by Anees
23/5/20 | 10000 |  |  | paid to Raphel - Interlock balance
27/5/20 | 32000 |  |  | Nilambur furniture - balance
27/5/20 | 3100 |  |  | Three bills by Anees
28/5/20 | 32600 |  |  | House warming food
28/5/20 | 10000 |  |  | Pastor
28/5/20 | 65000 |  |  | Anish - Aluminium fabrication
30/5/20 | 7500 |  |  | Videon - water level controller
31/5/20 | 3500 |  |  | AC shifting & installation
2020-02-06 | 4000 |  |  | Anees Plumbing
2020-03-06 | 19130 |  |  | Top floor shower + tap
2020-03-06 | 12306 |  |  | ForHome
2020-04-06 | 100000 |  |  | Saimon - Truss work - Advance
2020-04-06 | 3000 |  |  | Anees Electrical
2020-04-06 | 16000 |  |  | Anson - curtain - balance
2020-04-06 | 1508 |  |  | ForHome
2020-04-06 | 2852 |  |  | ForHome
2020-04-06 | 10000 |  |  | Kitchen Appliances - balance
2020-05-06 | 25000 |  |  | Mosquito Net - balance
2020-05-06 | 3886 |  |  | Anees (6 bills)
2020-06-06 | 500 |  |  | Top floor toilet window glass
2020-06-06 | 174 |  |  | 1 bill
2020-06-06 | 8000 |  |  | Anees (Plumbing)
2020-09-06 | 25000 |  |  | Cctv advance
2020-10-06 | 17000 |  |  | cctv balance
2020-10-06 | 280 |  |  | Carpet
2020-12-06 | 8700 |  |  | Anson - curtain
13/6/20 | 2495 |  |  | Curtain cloth
14/6/20 | 25000 |  |  | Tvm work
16/6/20 | 8000 |  |  | Nilambur Furniture Balance
16/6/20 | 20000 |  |  | Saimon - Work area Advance
16/6/20 | 6000 |  |  | plumbing materials by Anees
17/6/20 | 5000 |  |  | Anees (plumbing)
20/6/20 | 14000 |  |  | Simon - Welding
24/6/20 | 200000 |  |  | paid to Martin
27/6/20 | 4039 |  |  | Toilet fittings - kkp metals
28/6/20 | 16000 |  |  | Rent balance to Suresh, Tvm
28/6/20 | 7000 |  |  | CCTV Balance
30/6/20 | 1000 |  |  | Saimon
30/6/20 | 2000 |  |  | Anson -curtain
2020-03-07 | 25000 |  |  | Babu, Tvm
2020-04-07 | 10000 |  |  | Saimon
2020-04-07 | 23000 |  |  | Babu, Tvm
2020-05-07 | 25000 |  |  | Babu, Tvm
2020-06-07 | 4000 |  |  | Babu, Tvm
2020-07-07 | 3000 |  |  | Mosquito Net balance
2020-07-07 | 100000 |  |  | Balconu upvc work
2020-09-07 | 0 |  |  | Wadrobe work Advance (paid Rs. 80000/- returned on10/8/20
13/7/20 | 2000 |  |  | Anees (plumbing)
17/7/20 | 1500 |  |  | Anees (for purchase from Anitha) (1000+500)
17/7/20 | 2000 |  |  | Water connection charge
17/7/20 | 2000 |  |  | Anees (account not clear)
18/7/20 | 30000 |  |  | Simon
18/7/20 | 30000 |  |  | Simon (through bank)
18/7/20 | 13000 |  |  | given to Anees for purchase
18/7/20 | 4000 |  |  | Anees plumbing
20/7/20 | 7422 |  |  | kseb appln fee
20/7/20 | 100000 |  |  | Saimon - Sheet purchase
22/7/20 | 5000 |  |  | Anees (Plumbing)
25/7/20 | 10000 |  |  | Anees (plumbing)
25/7/20 | 10000 |  |  | Saimon
25/7/20 | 7000 |  |  | Saimon
28/7/20 | 115000 |  |  | Solar panel + Solar Heater
2020-04-08 | 23000 |  |  | Simon
2020-04-08 | 10000 |  |  | Edison - Advance
2020-08-08 | 20000 |  |  | Saimon
2020-10-08 | 6000 |  |  | Solar kseb deposit
2020-10-08 | 100000 |  |  | Solar installation (in cash)
2020-10-08 | 15000 |  |  | Balcony work (Falcon)
2020-10-08 | 8000 |  |  | Saimon
2020-12-08 | 10000 |  |  | Saimon
13/8/20 | 500 |  |  | Saimon
14/8/20 | 5500 |  |  | Saimon
15/8/20 | 90000 |  |  | Falcon
15/8/20 | 20000 |  |  | Saimon
22/8/20 | 55000 |  |  | Saimon
22/8/20 | 3000 |  |  | Saimon - tip
22/8/20 | 20000 |  |  | Edison
29/8/20 | 20000 |  |  | Saimon
29/8/20 | 5000 |  |  | Anees - purchase
29/8/20 | 2000 |  |  | Anees
2020-08-09 | 10000 |  |  | Saimon
2020-10-09 | 3500 |  |  | Gas pipe line - Abhilash
2020-10-09 | 1500 |  |  | Anees
2020-12-09 | 15000 |  |  | Anees
15/9/20 | 20000 |  |  | Saimon through account
16/9/20 | 25000 |  |  | Babu - Tvm
17/9/20 | 6000 |  |  | Babu - Tvm
18/9/20 | 2000 |  |  | Anees
18/9/20 | 100000 |  |  | Martin
20/9/20 | 6000 |  |  | Anees
21/9/20 | 25000 |  |  | Saimon
26/9/20 | 5000 |  |  | Solar team - Libin
26/9/20 | 24000 |  |  | Simon - balance (Gate+roof)
27/9/20 | 18500 |  |  | Stove
29/9/20 | 5000 |  |  | Anees
30/9/20 | 3000 |  |  | Anees
30/9/20 | 1500 |  |  | Anees
2020-03-09 | 8200 |  |  | Anees (3000 കടം)
2020-10-10 | 22000 |  |  | Simon (Fabricated stair roof)
2020-10-10 | 5000 |  |  | Simon (advance - sunshade support)
29/10/20 | 4300 |  |  | Anson - curtain work
30/10/20 | 2600 |  |  | Toilet door
14/11/20 | 11500 |  |  | Kitchen cabinet (250/- extra to be accounted later)
14/11/20 | 35000 |  |  | Salar panel balance
14/11/20 | 19810 |  |  | Edison balance
15/11/20 | 300000 |  |  | Martin
Total | 11766940 |  |  |  | 1922034
|  |  |  | balance | 751,702
Martin | 6003800 |  |  | Martin Account.
Josettan | 383500 |  |  | upto | 18/9/20 | 5703800
Archi | 146270 |  |  | adjustments |  | 170000
Aneesh | 226000 |  |  | Total paid |  | 5873800
Interior | 15000 |  |  | Bill total |  | 6567340
Plumbing | 240000 |  |  | Balance |  | 693540
Kichen Cabinet | 130000 |  |  | paid | 15/11/20 | 300000
Grill welding | 11300 |  |  | balance |  | 393540
Fabricated Stair | 33500
Stair Hand Rail | 45500 |  |  |  | Anees labour
False Ceiling | 32000
Handrail internal | 35000
Nilambur Furniture | 132000 |  |  |  | previous | 1+1
Divine doors | 104095 |  |  |  | previous | 2
Saimon (Truss work) | 409000 |  |  |  | 2020-10-09 | 1+1
Balcony work | 205000 |  |  |  | 2020-11-09 | 1+1
| 8678583 |  |  |  | 2020-12-09 | 1+1
|  | 0 |  |  | 16/9/20 | 1+1
[5 empty] | 17/9/20 | 1+1
[5 empty] | 18/9/20 | 1+1
8678583
Saimon | 465280
balance | 56280
Saimon (Gate-2+roof) | 99000

## Wiring
| Nos | Myrius (rate) | Total Myrious) | Arteor (graphite) | with GST |  | Ellis Esq (White) |  | Ellis Esq (Grey)
8 Module Plate | 28 | 117.6 | 3292.8 | 117.6 | 138.768 | 3885.504 | 95.87 | 2684.36 | 156.01 | 4368.28
6 Module Plate | 25 | 90.62 | 2265.5 | 90.62 | 106.9316 | 2673.29 | 79.15 | 1978.75 | 123.46 | 3086.5
4 Module Plate | 12 | 59.47 | 713.64 | 59.47 | 70.1746 | 842.0952 | 59.24 | 710.88 | 92.7 | 1112.4
3 Module Plate | 22 |  | 0 |  | 0 | 0 | 50.65 | 1114.3 | 84.11 | 1850.42
2 Module Plate | 12 |  | 0 |  | 0 | 0 | 38.44 | 461.28 | 63.31 | 759.72
6A/10A one way switch | 120 | 54.71 | 6565.2 | 76.8 | 90.624 | 10874.88 | 22.49 | 2698.8 | 32.13 | 3855.6
6A/10A two way switch | 35 | 86.09 | 3013.15 | 108 | 127.44 | 4460.4 | 62.4 | 2184 | 68.74 | 2405.9
6A/10A plug socket | 65 | 166.8 | 10842 | 185.6 | 219.008 | 14235.52 | 74.61 | 4849.65 | 82.29 | 5348.85
Step regulator | 8 | 367.69 | 2941.52 | 549 | 647.82 | 5182.56 | 239.67 | 1917.36 | 263.64 | 2109.12
16A one way switch | 15 | 136.3 | 2044.5 | 146.4 | 172.752 | 2591.28 |  | 0 |  | 0
16A plug socket | 9 | 166.8 | 1501.2 | 185.6 | 219.008 | 1971.072 | 110.79 | 997.11 | 122.09 | 1098.81
Dummy | 18 |  | 0 |  | 0 | 0 |  | 0 |  | 0
Mega bell push | 1 | 167.7 | 167.7 | 213.6 | 252.048 | 252.048 |  | 0 |  | 0
Mega two way switch | 1 |  | 0
|  |  | 33347.21 |  |  | 46968.6492 |  | 19596.49 |  | 25995.6
0
Hall, Dining & Office |  |  | 0
8 Module Plate | 6 | 117.6 | 705.6 |  | 0 | 0 | 95.87 | 575.22 | 156.01 | 936.06
6 Module Plate | 11 | 90.62 | 996.82 |  | 0 | 0 | 79.15 | 870.65 | 123.46 | 1358.06
4 Module Plate | 2 | 59.47 | 118.94 |  | 0 | 0 | 59.24 | 118.48 | 92.7 | 185.4
3 Module Plate | 4 |  | 0 |  | 0 | 0 | 50.65 | 202.6 | 84.11 | 336.44
2 Module Plate | 4 |  | 0 |  | 0 | 0 | 38.44 | 153.76 | 63.31 | 253.24
10A one way switch | 57 | 54.71 | 3118.47 | 76.8 | 90.624 | 5165.568 | 22.49 | 1281.93 | 32.13 | 1831.41
10A two way switch | 12 | 86.09 | 1033.08 | 108 | 127.44 | 1529.28 | 62.4 | 748.8 | 68.74 | 824.88
10A plug socket | 20 | 166.8 | 3336 | 185.6 | 219.008 | 4380.16 | 74.61 | 1492.2 | 82.29 | 1645.8
Step regulator | 3 | 367.69 | 1103.07 | 549 | 647.82 | 1943.46 | 239.67 | 719.01 | 263.64 | 790.92
16A one way switch | 3 | 136.3 | 408.9 | 146.4 | 172.752 | 518.256 |  | 0 |  | 0
16A plu socket | 2 | 166.8 | 333.6 | 185.6 | 219.008 | 438.016 | 110.79 | 221.58 | 122.09 | 244.18
Dummy | 8 |  | 0 |  | 0 | 0 |  | 0 |  | 0
Bell push | 1 | 167.7 | 167.7 | 213.6 | 252.048 | 252.048 |  | 0 |  | 0
0
0
0
Insulation tape | 20 |  | 0
10A stip connector (bar) | 25 |  | 0
Wire tie No. 150 (packet) | 3 |  | 0
Wire tie No. 200 (packet) | 2 |  | 0
0
0
|  |  | 11322.18 |  |  | 14226.788 |  | 6384.23 |  | 8406.39
|  | Total | 44669.39 |  |  | 61195.4372 |  | 25980.72 |  | 34401.99

## Door
nos
Toilet | 7000 | 9 | 63000
Other Doors
Ground floor | 3500 | 3 | 10500
First floor | 3500 | 2 | 7000
| 5000 | 1 | 5000
Second floor | 3500 | 3 | 10500
96000

## Pending Works
1. false celing - 3 places
2. Kitchen primar & putty
3. First floor - washing machine, wash basin, sink (plumbing)
4. Tile dust in office room
5. TV screen cladding stone
6. Water grating - Garden - dining room
7. small hooks

## JK
Account (SBI) | 250000
In hand | 600000
Account (Co-op) | 233551
Account (Co-op) | 127027
Account (Co-op) | 273834
1484412

## FD
SBI | 522167 | 4
SBI | 519179 | 1
SBI | 503623 | 3
SBI | 503623 | 2
Co-op | 250000 | 1
Co-op | 175000 | 1
Co-op | 175000 | 1
5725962

## Balance in hand
7210374